## Components 2&3
|  |  | Country/Organisation:West Bank & Gaza /NDC |  | Loan #: TF057872
Project/Programme:Palestinian NGO III
Request for EOI (where required)
[7 empty] | Preparation Request for Proposals |  |  |  | Short List |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotions (N) |  |  |  | Draft Contract |  | Contract Finalization |  | Contract Implementation
Item Number | Sub Component Number | Package Code | Description* | Selection Method | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Preparation Eval Report (T) (F) | Negotiations (N) | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
Component 2: Sector Development
1 | 2.1 | 01 SD-C-07 | Transperancy and Accountability System | SS | Prior | Plan | [15 empty] | 18 Aug 07 | 20 Aug 07
[6 empty] | Actual | 28 Apr 07 | 07 May 07 | NA | NA | NA | NA | 31 May 07 | 12 Jun 07 | NA | NA | NA | 25 Jul 07 | 06 Aug 07 | 13 Aug 07
2 | 2.1 | 02 SD-C-07 | Resource Kit Development | CQS | Prior | Plan | [7 empty] | 18 Aug 07 | 25 Aug 07 | NA | NA | 03 Sep 07 | 06 Sep 07 | 12 Sep 07 |  | 13 Sep 07 | 18 Sep 07
[6 empty] | Actual | 20 May 07 | 05 Jun 07 | 07 Jun 07 | 15 days | 17 July 07* | 30 July 07 | 04 Aug 07
3 | 2.1 | 03 SD-C-07 | Design and Print promotional Campaign | CQS | Prior | Plan | [6 empty] | 18 Aug 07 | 01 Sep 07 | 08 Sep 07 | NA | NA | 15 Sep 07 | 17 Sep 07 | 24 Sep 07 |  | 25 Sep 07 | 29 Sep 07
[6 empty] | Actual | 16 Jun 07 | 27 Jun 07 | 025 Jul 07 | 14 days | 11 Aug 07 | 13 Aug 07
4 | 2.1 | 04 SD-C-07 | Conduct Need Assessment & Prepare Development Plans | QCBS | Prior | Plan | 03 Sep 07 | 13 Sep 07 | 15 Sep 07 | 14 days | 03 Oct 07 | 8 Oct 07 | 09 Oct 07 | 07 Nov 07 | 13 Nov 07 | 19 Nov 07 | 22 Nov 07 | 27 Nov 07 | 28 Nov 07 | 03 Dec 07 |  | 04 Dec 07 | 05 Dec 07
Actual
5 | 2.1 | 05 SD-C-07 | Providing Technical Assistant to 10 NGOs in North West Bank,Middle West Bank and South West Bank (3 contracts) | QCBS | Prior | Plan | 15 Dec 07 | 20 Dec 07 | 24 Dec 07 | 14 days | 14 Jan 08 | 21 Jan 08 | 23 Jan 08 | 23 Feb 08 | 06 Mar 08 | 11 Mar 08 | 13 Mar 08 | 15 Mar 08 | 17 Mar 08 | 20 Mar 08 |  | 22 Mar 08 | 25 Mar 08
Actual
6 | 2.1 | 06 SD-C-07 | Providing Technical Assistant to 20 NGOs in Gaza Strip | QCBS | Prior | Plan | 15 Dec 07 | 20 Dec 07 | 24 Dec 07 | 14 days | 30 Jan 08 | 04 Feb 08 | 07 Feb 08 | 06 Mar 08 | 13 Mar 08 | 20 Mar 08 | 22 Mar 08 | 29 Mar 08 | 31 Mar 08 | 03 Apr 08 |  | 05 Apr 08 | 07 Apr 08
Actual
7 | 2.2 | 07 SD-C-07 | Set up networks performance standards of the 4 UMBRELLA networks and the three thematic networks | IC | Prior | Plan | 18 Aug 07 | 24 Aug 07 | NA | NA | 05 Sep 07 | 12 Sep 07 | NA | NA | 15 Sep 07 | 20 Sep 07 | NA | 22 Sep 07 | 24 Sep 07 | 27 Sep 07 |  | 29 Sep 07 | 01 Oct 07
Actual
8 | 2.3 | 08 SD-C-07 | Promoting cooperation between NGOs and the Private Sector | IC | Post | Plan | 29 Sep 07 | NA | 01 Oct 07 | 14 days | 18 Oct 07 | NA | NA | NA | 22 Oct 07 | NA | NA | 24 Oct 07 | 25 Oct 07 | NA |  | 27 Oct 07 | 31 Oct 07
Actual
9 | 2.3 | 09 SD-C-08 | Research on tracking donor funds to Palestinian NGOs | IC | Prior | Plan | 01 Mar 08 | 06Mar 08 | 10 Mar 08 | 14 days | 27 Mar 08 | 31 Mar 08 | NA | NA | 01 Apr 08 | 09 Apr 08 | NA | 15 Apr 08 | 16 Apr 08 | 22 Apr 08 |  | 24 Apr 08 | 01 May 08
Actual
Component 3: Institutional Development
10 | 3.1 | 10 ID-C-07 | Consultancy services to support Events Organization (3) | IC | Post | Plan | 05 Sep 07 | NA | NA | NA | 19 Sep 07 | Na | NA | NA | 25 Sep 07 | NA | NA | 29 Sep 07 | 01 Oct 07 | NA |  | 02 Oct 07 | 17 Oct 07
Actual
11 | 3.1 | 11 ID-C-07 | Consulting Service in support of resource mobilization | IC | Post | Plan | 30 Aug 07 | NA | NA | NA | 15 Sep 07 | NA | NA | NA | 19 Jun 07 | NA | NA | 20 Sep 07 | 24 Sep 07 | NA |  | 26 Sep 07 | 01 Oct 07
Actual
12 | 3.2 | 12 ID-C-08 | Development and Training for MIS for M & E | QCBS | Prior | Plan | 08 Jan 08 | 15 Jan 08 | 16 Jan 08 | 14 days | 04 Feb 08 | 07 Feb 08 | 09 Feb 08 | 08 Mar 08 | 13 Mar 08 | 20 Mar 08 | 24 Mar 08 | 07 Apr 08 | 08 Apr 08 | 15 Apr 08 |  | 19 Apr 08 | 21 Apr 08
Actual
13 | 3.2 | 13 ID-C-08 | Evaluation of MIS | IC | Post | Plan | 03 May 08 | NA | 05 May 08 | 14 days | 22 May 07 | NA | NA | NA | 26 May 08 | NA | NA | 29 May 08 | 31 May 08 | NA |  | 02 Jan 08 | 03 Jan 08
Actual
14 | 3.3 | 14 ID-C-07 | Procurement Trainer for Staff and grants recipients | IC | Post | Plan | 01 Nov 07 | NA | NA | NA | 10 Nov 07 | NA | NA | NA | 15 Nov 07 | NA | NA | 20 Nov 07 | 26 Nov 07 | NA |  | 28 Nov 07 | 01 Dec 07
Actual
15 | 3.3 | 15 ID-C-07 | Financial Management Trainer for Staff and grants recipients | IC | Post | Plan | 15 Sep 07 | NA | NA | NA | 27 Sep 07 | NA | NA | NA | 02 Oct 07 | NA | NA | 03 Oct 07 | 04 Oct 07 | NA |  | 08 Oct 07 | 10 Oct 07
Actual
16 | 3.3 | 16 ID-C-07 | M&E Trainer for Staff and grants recipients | IC | Post | Plan | 15 May 08 | NA | NA | NA | 27 May 08 | NA | NA | NA | 02 Jun 08 | NA | NA | 04 Jun 08 | 05 Jun 08 | NA |  | 07 Jun 08 | 09 Jun 08
Actual
17 | 3.3 | 17 ID-C-07 | Financial and external Audits | LCS | Prior | Plan | 23 Aug 07 | 30 Aug 07 | 01 Sep 07 | 14 days | 15 Sep 07 | 24 Sep 07 | 25 Sep 07 | 01 Nov 07 | 05 Nov 07 | 08 Nov 07 | 14 Nov 07 | 20 Nov 07 | 21 Nov 07 | 26 Nov 07 |  | 27 Nov 07 | 29 Nov 07
Actual
18 | 3.3 | 18 ID-C-07 | External Audit (Projects) | LCS | Prior | Plan | 19 Jul 07 | 26 Jul 07 | 30 Jul 07 | 14 days | 16 Aug 07 | 23 Aug 07 | 27 Aug 07 | 27 Sep 07 | 04 Oct 07 | 11 Oct 07 | 18 Oct 07 | 25 Oct 07 | 01 Nov 07 | 06 Nov 07 |  | 10 N ov 07 | 17 Nov 07
|  |  | FROZEN, Merged with the financial Audits |  |  | Actual
19 | 3.3 | 19 ID-C-07 | Technical Assistance to support NDC Management (4 contracts) | IC | Post | Plan | 28 Aug 07 | NA | 01 Sep 07 | 14 days | 17 Sep 07 | NA | NA | NA | 19 Sep 07 | NA | NA | 20 Sep 07 | 22 Sep 07 | NA |  | 01 Oct 07 | 02 Oct 07
Actual
20 | 3.3 | 20 ID-C-07 | Leagal Advisor | IC | Prior | Plan
[6 empty] | Actual | 12 May 07 | 21 May 07 | NA | NA | 29 May 07 | 30 May 07 | NA | NA | 29 May 07 | 30 May 07 | NA | 19 Jun 07 | 21 Jun 07 | 24 Jun 07 | 4.8 | 25 Jun 07 | 27 Jun 07
Total Cost | [20 empty] | #REF! | [5 empty] | #REF!
[21 empty] | 0 | [5 empty] | 0
* The evaluation form was submitted again on 30 July after incorporating the Bank's comment

## Goods and Works
|  | Country/Organisation:West Bank & Gaza /NDC |  |  |  | Loan #: TF057872
|  | Project/Programme:PNGO III | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
|  |  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation
# | Sub Component Number | Description* | Package Number | Lot Number | Package Code | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Contract Amount in US$'000 | Date Contract Award | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Goods- List of Contracts
1 | 3.1 | Publication to support resource mobbilization* | 1 | NA | 01 ID-G-07 | S | Post | Prior | Plan |  |  | NA | [7 empty] | NA
[9 empty] | Actual | 16 May 07 | 21 May 07 |  | 26 May 07 | 05 Jun 07 | 12 Jun 07 | 17 Jun 07 |  | 18 Jun 07 | 01 Jul 07
2 | 3.3 | Gaza Office equipment | 1 | NA | 02 ID-G-07 | S | Post | Prior | Plan | 15 Aug 07 | 22 Aug 07 | NA | 23 Aug 07 | 03 Sep 07 | 08 Sep 07 | 11 Sep 07 |  | 12 Sep 07 | 13 Sep 07 | NA
Actual
3 | 2.1 | Print the resource kit* | 1 | NA | 03 SD-G-07 | S | Post | Prior | Plan | 03 Nov 07 | 07 Nov 07 | NA | 08 Nov 07 | 22 Nov 07 | 24 Nov 07 | 27 Nov 07 |  | 29 Nov 07 | 01 Dec 07 | NA
Actual
4 | 3.2 | Dissemination & Publication for MIS* | 1 | NA | 04 ID-G-07 | S | Post | Post | Plan | 25 Oct 07 | NA | NA | 01 Nov 07 | 17 Nov 07 | 22 Nov 07 | NA |  | 24 Nov 07 | 26 Nov 07 | NA
Actual
5 | 3.3 |  | 1 | NA | 06 ID-G-07 | S | Post | Prior | Plan | 20 Aug 07 | 22 Aug 07 | NA | 23 Aug 07 | 06 Sep 07 | 08 Sep 07 | 11 Sep 07 |  | 12 Sep 07 | 15 Sep 07 | NA
|  | Gaza Office Furniture | [6 empty] | Actual
6 | 3.3 | Gaza Office electical equipments | 1 | NA | 07 ID-G-07 | S | Post | Post | Plan | 24 Aug 07 | NA | NA | 25 Aug 07 | 08 Sep 07 | 10 Sep 07 | NA |  | 13 Sep 07 | 17 Sep 07 | NA
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Total Cost | [8 empty] | Plan | [7 empty] | 0
[9 empty] | Actual | [7 empty] | 0
* works